## Sheet1
Project Name: |  | POS | Assigned To: | RI7761 | Browsers: | Microsoft Edge, Google Chrome | Status |  | Severity-Priority
Date: |  | 2024-10-03 | Tested By: | Anik Rahman |  |  | Open | Released | High
Created By: |  | Anik Rahman |  |  |  |  | In Progress | Closed | Medium
[7 empty] | Complete |  | Low
Date | Bug ID | Bug Title | Bug Description | Severity-Priority | Assigned | Status | Verified and Closed | Comment | RAC | Attachment
2024-10-03 | POS_002 | Phone number takes char as it's value | In Order Now form Phone Number field takes character as its input | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_004 | Shipping address field accept only 1 character without error | In order Now form Shipping address field displays no error while giving only one character as its input | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_005 | A small section opens just below Dashboard & Backup while hovering | In portfolio section Dashboard & Backup option shows a small section while hovering over | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_007 | Subject accepts only one string without showing error | In Contact form Subject field accepts one string and shows no error message | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_008 | Message field accepts only one string without any error | In Contact form Message field accepts one string and shows no error message | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_009 | Show Password checkbox not working | In User Authentication (https://freepos123.com/authentication/) show password checkbox not working. | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_010 | Download button unresponsive with incomplete email format | In Guest download if email field input remains incomplete and click download then button is unresponsive and no error message shows | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_011 | Session Inconsistency: Able to Download Files After Logout in Another Tab | After successful login if user logged out in another tab still user can download POS system in the first tab. | High | RI7761 | Open |  |  | Auto download feature not implemented | #VALUE!
2024-10-03 | POS_012 | Last 2 image of swipe gallery not showing properly | In Portfolio section, Authentication swipe gallery have 3 image. Last 2 image not showing properly | Medium | RI7761 | Open |  |  |  | #VALUE!
2024-10-03 | POS_013 | Spelling mistake in the pricing section | There is a spelling mistake in the pricing section in 'Standard' Plan | Low | RI7761 | Open